Minutes of the Meeting of Staverton Neighbourhood Development Plan Committee

Thursday 22nd September 2016 at Staverton Village Hall

Present: R Frost (RF), J Gilford (JMG), T Glover (ToG), J Vale (JV), I Weaver (IW),

Clerk – S Porter, Members of the public – Nil

- CHAIRMAN’S ANNOUNCEMENTS

1.1	Apologies received – K Edwards (KE), J Golding (JFG), J Holliday

1.2	Subsequent announcements – Nil

2	GOVERNANCE

2.1	Declaration and nature of interest – The Register of Members Interest form will be completed by all, which will be amended by the Clerk, to suit the requirements of the SNDP.

2.2	Consideration of dispensation requests received – There will be a dispensation request submitted to the Parish Council for all the Parish Council members on the committee.

3         APPROVE MINUTES of the Meeting held on the 13th September 2016 – It was agreed by all that these were a true and correct record.

4	MATTERS ARISING

4.1	Slip to be printed and distributed to all households advising of cancellation of the consultation event on the 17th September 2016 – This has been completed.

4.2	Response to be sent to developer letter (Grainger) advising the same message that had been sent to all previous developers – This has been sent.

5	BUSINESS ARISING

5.1 	Consultation event 1st October 2016

| Ref | Task | Responsible person | Status |
| --- | --- | --- | --- |
| 5.2 | Village Hall availability checked | KE | Completed |
| 5.3 | Refreshments facilitated | JH | Arranged |
| 5.4 | Presentation format produced | JMG | Completed |
| 5.5 | Sites agreed | All | Completed |
| It was agreed by all the 3 sites that will be included in the consultation. |
| 5.6 | Leaflet produced for promotion of event | ToG | Approved |
| ToG has produced the leaflet which will be distributed to all properties in the Parish. 220 will be printed. |
| 5.7 | Date for leaflet drop agreed | All | Approved |
| The leaflets will be distributed the weekend of 24/25 September. |
| 5.8 | Assignment of leaflet delivery lists | All | Designated |
| Each committee member was allocated roads and properties to deliver and these will be confirmed in an e-mail from ToG. |
| 5.9 | Voting procedure agreed | All | Agreed |
| The voting slip will be given out, 1 per person. There will be one cross required on each slip. |
| 5.10 | Production of voting slips | ToG | Agreed |
| 5.11 | Electoral roll list produced | JH | Arranged |
| 5.12 5.13 | Display material produced Maps Questionnaire analysis | ToG JMG | Approved |
| 5.14 | Display equipment facilitated Projector & cabling Laptop Screen Display boards | ToG ToG ToG ToG | Arranged |

6	PRODUCTION OF STATUTORY DOCUMENTS

6.1	Development Plan – Defer to the next meeting

| Ref | Task | Responsible person | Status |
| --- | --- | --- | --- |
| 6.1.1 | Foreword | JMG | Completed |
| 6.1.2 | Introduction & Background | KE |  |
| 6.1.3 | Process summary | KE |  |
| 6.1.4 | Vision & Goals | ToG |  |
| 6.1.5 | Staverton our village | JG |  |
| 6.1.6 | National and local context | RF |  |
| 6.1.7 | Neighbourhood Plan | All |  |
| 6.1.8 | Community policies | JMG |  |
| 6.1.9 | Environment Policies | JMG |  |
| 6.1.10 | Design Statement | JG |  |
| 6.1.11 | Conservation Area | JH |  |
| 6.1.12 | Development Plan | IW |  |

6.2	Consultation Statement – Defer to the next meeting

| Ref | Task | Responsible person | Status |
| --- | --- | --- | --- |
| 6.2.1 | Introduction | JG |  |
| 6.2.2 | Background information and timeline | ToG |  |
| 6.2.3 | Working Group | ToG |  |
| 6.2.4 | Questionnaire | JMG | Completed |
| 6.2.5 | Questionnaire Results | JMG | Completed |
| 6.2.6 | First draft plan |  |  |
| 6.2.7 | Draft Plan |  |  |
| 6.2.8 | Pre-submission plan |  |  |
| 6.2.9 | Ongoing review |  |  |

7.	It has been agreed that JFG will produce the toolkit for the sites.

8.	DATE OF FUTURE MEETINGS 	 	Tuesday 27th September 2016

Saturday 1st October 2016

Thursday 6th October 2016

Tuesday 18th October 2016

Thursday 3rd November 2016

Tuesday 15th November 2016

Tuesday 29th November 2016

Tuesday 13th December 2016

Meeting Closed: 8:50pm